## Jira Backlog
Issue ID | Title | Description | Story Points | Assignee | Branch Name | Sprint
TR-1 | Project Setup | Initialize Flask project and repository structure | 3 | Shivam | feature/project-setup | Sprint 1
TR-2 | Install NLP Model | Integrate Helsinki-NLP/opus-mt-en-hi model using transformers | 5 | Aman | feature/model-integration | Sprint 1
TR-3 | Create Flask API | Build backend route to accept English text and return Hindi translation | 5 | Riya | feature/flask-api | Sprint 1
TR-4 | Frontend UI | Create HTML page with text input and translate button | 3 | Neha | feature/frontend-ui | Sprint 1
TR-5 | Display Translation | Show translated Hindi output on webpage | 2 | Aman | feature/output-display | Sprint 1
TR-6 | Error Handling | Handle empty input and invalid requests | 2 | Riya | feature/error-handling | Sprint 2
TR-7 | Add CSS Styling | Improve UI with CSS styling | 2 | Neha | feature/ui-styling | Sprint 2
TR-8 | API Optimization | Optimize model loading and response speed | 5 | Shivam | feature/performance-optimization | Sprint 2
TR-9 | Testing | Write test cases for translation functionality | 3 | Aman | feature/testing | Sprint 2
TR-10 | Prepare requirements.txt | Add required libraries for deployment | 1 | Riya | feature/requirements-file | Sprint 2
TR-11 | Render Deployment | Deploy Flask application on Render platform | 5 | Shivam | feature/render-deployment | Sprint 3
TR-12 | Documentation | Write README and deployment guide | 2 | Neha | feature/documentation | Sprint 3